## Sheet1
A conservation project
Project activity report
for the period 1 Jan 2018 - 30 Jun 2021
Code | Description | Actual- YTD | Budget - YTD | Variance | Variance % | Full Year Budget
Human resources
A01 | Program manager | 5138.92 | 5000 | 138.92 | 2.78% | 10000
A02 | Field Manager | 2189.73 | 2200 | -10.27 | -0.47% | 4400
A03 | Field Coordinators | 1759.52 | 1750 | 9.52 | 0.54% | 3500
A04 | Administrators | 763.98 | 1500 | -736.02 | -49.07% | 3000
A05 | Field Leaders | 4273.73 | 3600 | 673.73 | 18.71% | 7200
A07 | Finance Manager | 573.92 | 1500 | -926.08 | -61.74% | 3000
| Subtotal | 14699.8 | 15550 | -850.2 | -5.47% | 31100
Travel & transport
B01 | International flights - project monitoring | - | 2500 | -2500 | -100% | 5000
B02 | Loca travel | 3173.76 | 3500 | -326.24 | -9.32% | 4000
B03 | Fuel | 1235.45 | 1750 | -514.55 | -29.4% | 2100
B04 | Vehicle maintenance and repair | 2237.65 | 1500 | 737.65 | 49.18% | 2000
| Subtotal | 6646.86 | 9250 | -2603.14 | -28.14% | 13100
Equipment & supplies
C01 | Vehicle | 24763.98 | 35000 | -10236.02 | -29.25% | 35000
C02 | Motorcycles | 12856.47 | 15000 | -2143.53 | -14.29% | 15000
C03 | Laptops | 8125.78 | 7500 | 625.78 | 8.34% | 7500
C04 | Camera traps | 1954.76 | 2750 | -795.24 | -28.92% | 2750
C05 | First aid and medical supplies | 628.45 | - | 628.45 | 0% | 0
| Subtotal | 48329.44 | 60250 | -11920.56 | -19.79% | 60250
Other costs
E01 | Baseline assessment | 2435 | 1500 | 935 | 62.33% | 1500
E02 | Remote montioring | 1439.48 | 2200 | -760.52 | -34.57% | 3500
E03 | Land assessment | 1849.3 | 2000 | -150.7 | -7.54% | 2000
E04 | Community consultations | 1953.48 | 750 | 1,203 48 | 160.5% | 1000
E05 | Training workshops | 1743.97 | 1000 | 743 97 | 74.4% | 1000
E06 | Conservation awareness events | 1128.59 | 500, 00 | 628 59 | 125.7% | 2500
E07 | Publication of findings | - | - | - | 0% | 1750
E08 | Audit fee | 1250 | - | 1.250.00 | 0% | 1250
E09 | Bank charges | 74.32 | 500 | -425.68 | -85.14% | 1000
E10 | Interpreters | 1382.47 | 850 |  | 62.62% | 950
E11 | Document translation | - | 250 |  | -100% | 850
E12 | Traffic fines | 225 | - |  | 0% | 0
| Subtotal | 13481.61 | 9550 | 3931.61 | 41.17% | 17300
| Total expenditure | 83157.71 | 94600 | -11442.29 | -12.1% | 121750
Note on C5: Bobbi Hope: This column shows total expenditure for the year to date (which is six months into the project)
Note on D5: Bobbi Hope: This column shows the budget at this stage of the project (six months in; half way through)
Note on G5: Bobbi Hope: This column shows the total budget for the year
Note on C8: Bobbi Hope: These salaries are all very close to half the full year budget. Nothing to worry about here!
Note on D11: Bobbi Hope: Administrators salaries is only half spent – did they only recruit one?
Note on F13: Bobbi Hope: The finance manager salary is only 40% spent – are they not utilising them?
Note on C17: Bobbi Hope: There's been no spend on international flights – why not?
Note on B20: Bobbi Hope: Vehicle maintenance is well overspent – has the vehicle been out of commission? Have activities been delayed as a result? Information like this in a budget can be an indicator of problems beyond just financial ones.
Note on D20: Bobbi Hope: Many donors will allow organisations to move a certain amount (e.g. 10% of a section total) of available budget without approval. This is known as virement. However this amount is probably outside a funder's virement policy.
Note on C24: Bobbi Hope: The vehicle cost was much lower than the budget. Did they buy a used vehicle? This could be why the maintenance costs are higher than what was budgeted.
Note on D24: Bobbi Hope: Vehicle and motorcycle costs have been overbudgeted. What are the plans for reallocating this budget?
Note on D28: Bobbi Hope: There was no budget for this. Will the funder allow this cost?
Note on D35: Bobbi Hope: There's a big overspend here. Are they having problems with the communities they are working with?
Note on C39: Bobbi Hope: A project will probably not have been audited in the first six months. Has this been mistakenly allocated?
Note on D41: Bobbi Hope: Overspent. How will these costs be covered?
Note on D43: Bobbi Hope: There was (maybe unsurprisingly) no budget for this. A funder is unlikely to refund this.